## Slide 1: Satellite Integration Report
Date

## Slide 2: Satellite Status report – Week of 2016-11-01 Reason for status: Major satellites on track, Issues being solved in Unit Test
Rating:
 Fully on track, no intervention needed
 Off-track, but a credible plan is in-place to get back on-track
 Off-track and no credible plan in-place to get back on-track. Intervention required.
 Completed.
Logistic Delivery Satellites – Unit Test (end-to-end) in progress
Dynasys UT closed
TMs Kewilll UT closed
Activities completed
Intervention or decision required | Raised by Interface | Responsible | Due by
Confirm Nutrade WeMap changes Feedback
Close Nutrade flat file ECC design
Close Nutrade GD design
Finalize GKO fixes
Evaluate decommissioning of AILOG
Activities for coming week
Data Objects Needed |  |  | 
COMM | PnS | FIP | Nut
Customer | Transport master data | Credit Limit | Transaction data
Material | Transaction data | Bank Data | Customer
Pricing | Carrier tracking data | Fiscally relevant transactional data | Material
Transaction data | Freight invoices | FI/CO-postings | 
 | Production orders |  | 

## Slide 3
Satellites | Data needed | Streams | Solution Readiness (RAG) | Environment Readiness (RAG) |  |  | Data Requirements identified (RAG) | Cutover Strategy (RAG)
 |  |  |  | IST | UAT | PROD |  | 
Agroview | NO (stand alone**) | COMM | G (stand alone) | N/A |  |  | N/A | R (Unknown)
PecSyn | YES | COMM | A (still in design phase) | A |  |  | A (MD/TD) | R (Unknown)
Plussoft SaaS | YES (MD) | COMM | G (flat file ready) | A |  |  | G (MD) | R (Unknown)
SPOT | YES (MD/TD) | COMM | R (stand alone - design on going) | A |  |  | A (MD/TD) | R (Unknown)
Teamspace (SIPExc mngt) | NO (stand alone**) | COMM | G (stand alone) | A |  |  | N/A | R (Unknown)
Bank Payment Processing | YES (TD) | FIP |  |  |  |  |  | 
Credito Rural | YES (MD/TD) | FIP | G (flat file ready) | G |  |  | G (MD/TD) | R (Unknown)
Easy IRPJ | YES (MD/TD) | FIP | G (flat file ready) | G |  |  | G (MD/TD) | R (Unknown)
HR | YES (MD) | FIP | G (interfaces ready) | G |  |  | G (MD) | R (Unknown)
MasterSAF DW | YES (MD/TD) | FIP | G (interfaces ready) | G |  |  | G (MD/TD) | G (MD full upload/refresh)
Payroll | ? | FIP |  |  |  |  |  | 
Rhadar Cartão de Visitar | YES (MD) | FIP | G (flat file ready) | G |  |  | G (MD) | R (Unknown)
Serasa | NO* | FIP | A (interface build in progress) | A |  |  | G (TD) | N/A
Synseg | YES (MD) | FIP | G (flat file ready) | G |  |  | G (MD) | R (Unknown)
TPS (Pricing) | YES (MD/TD) | FIP | A (flat file build in progress) | G |  |  | G (MD/TD) | R (Unknown)
TP-Tool / BW | YES (MD/TD) | FIP | A (interface build in progress) | A |  |  | G (MD/TD) | R (Unknown)
GD Nutrade | YES (MD/TD) | NuTrade | A (flat file in design) | A |  |  | A (in design) | R (Unknown)
ML Substitute | NO (stand alone**) | NuTrade | R (build plan unknown) | R |  |  | R (Unknown) | R (Unknown)
Monitoramento Logistico | NO (decomission) | NuTrade | N/A | N/A |  |  | N/A | N/A
WebMap | YES (MD/TD) | NuTrade | A (flat file build in progress) | A |  |  | G (MD/TD) | G (MD delta update)
Ailog | NO (on hold) | PnS | N/A | N/A |  |  | N/A | N/A
Carrier Web Services | NO* | PnS | A (interface in unit test) | G |  |  | G (TD) | N/A
Dynasys | YES (MD/TD) | PnS | A (flat file ready) | G |  |  | G (MD/TD) | G (MD manual maint)
GKO Frete | YES (MD/TD) | PnS | A (interface in unit test) | A |  |  | G (MD/TD) | G (MD delta upload)
One Source Global Trade | YES (MD/TD) | PnS | A (interface build in progress) | A |  |  | G (MD/TD) | R (Unknown)
Painel e-Kanban | NO (decomission) | PnS | N/A | N/A |  |  | N/A | N/A
TMS Kewill | YES (MD/TD) | PnS | A (interface ready) | G |  |  | G (MD/TD) | G (MD manual maint)
Toledo scale | NO* | PnS | G (flat file to Dynasys ready) | G |  |  | G (TD) | N/A
* No data is sent, just retrieved from Satellite
** Stand alone systems have data being inputed manually

## Slide 4: PnS Satellite Systems Landscapes

## Slide 5: DYNASYS / Toledo Scale Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Dynasys PROD
Before Go-live
Dynasys IST / UAT
Dynasys PROD
After Go-live
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
TOLEDO scale
Before Go-live
TOLEDO scale
After Go-live
(2)
2008 server
2008 server
LAD
EhP5
LAQ
EhP5
LAU
EhP5
Cutover steps:
Move ECC TRs
Business Cut off
Implement Changes in Dynasys PROD
Manually create MD in Dynasys PROD
Run Smoke test

## Slide 6: TMS Kewill Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
TMS PROD Before Go-live
TMS Sandbox
TMS PROD After Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Move ECC TRs
Business Cut off
Move PI/PO TRs
Connect TMS PROD to POP
Manually create MD in TMS
Run Smoke test
(1)
(3)
(2)
(4)
(5); (6)
TMS Sandbox
Inbound: WebS
Outbound: IDOC
Inbound: WebS
Outbound: IDOC
Inbound: WebS
Outbound: IDOC
IDOC
IDOC

## Slide 7: GKO Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
GKO PROD
Before Go-live
GKO Sandbox
GKO PROD
After Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Move ECC TRs
Business Cut off
Implement Changes in GKO
Move PI/PO TRs
Connect POP to FEP
Automatically create MD in GKO
Run Smoke test
(1)
(4)
(5)
(3); (6); (7)
ABAP Proxy
POD
POI
POU
POP
(2)
ABAP Proxy
ABAP Proxy
ABAP Proxy
CARRIERS
FTP
SEFAZ
SEFAZ
JDBC
JDBC
JDBC

## Slide 8: OneSource Global Trade Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
OSGT Dev
OSGT Prod
Cutover Steps:
Move ECC TRs
Move PI/PO TRs
Implement Changes in OSGT
Connect OSGT to POP
Automatically create MD in OSGT
Implement Changes in Configuration tables for OSGT
Run Smoke test
(1)
(2)
(4)
(3); (5); (7)
IDOC
IDOC
WS
WS
OSGT IST
OSGT UAT
WS
WS
(6)

## Slide 9: Carrier WebServices Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
Cutover Steps:
Move ECC TRs
Move PI/PO TRs
Business Cut off
Decommision Carrier WS
Map Carrier http and FTP links
Run Smoke test
(1)
(2)
(5)
(6)
IDOC
IDOC
CARRIERS
Carrier WS Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(3)
CARRIERS
(4)
RFC

## Slide 10: Status of Data Migration Strategy for PnS Satellite Systems (MASTER DATA)

## Slide 11: Status of Data Migration Strategy for PnS Satellite Systems (TRANSACTIONAL DATA)

## Slide 12: FiP Satellite Systems Landscapes

## Slide 13: HR (GPS) Satellite Landscape
TO-BE
AS-IS
GPS
Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover steps:
Business Cut Off
Move ECC TRs
Move HR TRs
Connect GPS to FEP
Run Smoke test
IDOC
GPT
Before Go-live
GPD
Before Go-live
(1)
IDOC
IDOC
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
(2)
(4);(5)
IDOC
IDOC
IDOC
IDOC
GPS
After Go-live
GPT
After Go-live
GPD
After Go-live
(3)

## Slide 14: Rhadar / Synseg Satellite Landscape
TO-BE
AS-IS
GPS
Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover steps:
GPS Cutover
Run Smoke test
GPT
Before Go-live
GPD
Before Go-live
Rhadar
Before Go-live
SynSEG
Before Go-live
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
IDOC
IDOC
IDOC
zTCD
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
IDOC
IDOC
IDOC
IDOC
GPS
After Go-live
GPT
After Go-live
GPD
After Go-live
(2)
Rhadar
After Go-live
SynSEG
After Go-live
(1)
zTCD

## Slide 15: GRC NFE Satellite Landscape
TO-BE
AS-IS
FFU
EhP7 SP12
FEP
EhP7 SP12
POD
POI
POU
POP
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Business Cut Off
Move ECC TRs
Move GRCNFE TRs
Move PI/PO TRs
Run Smoke test
(2)
(4)
LND
POD
POI
POU
POP
(1)
LNI
LNU
LNP
GND
GNI
GNU
LNP
(5)
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
FFD
EhP7 SP12
FFT
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
(3)

## Slide 16: MasterSAF DW Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
MSAF PRD
Cutover steps:
Business Cut Off
Move ECC TRs
Move MSAF AOL changes
Connect MSAF AOL to FEP
Run Smoke test
(2)
(4);(5)
MSAF QAS
MSAF DEV
MSAF AOL PRD
MSAF AOL QAS
MSAF AOL DEV
(1)
(1)
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
MSAF PRD
MSAF QAS
MSAF DEV
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(3)

## Slide 17: SERASA Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
POD
POI
POU
POP
Cutover Steps:
Move ECC TRs
Move PI/PO TRs
Map SERASA http links
Run Smoke test
(1)
(2)
(3)
(4)
IDOC
IDOC
WS?
SERASA
Review

## Slide 18: Credito Rural Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Crédito Rural before Go-live
Crédito Rural IST/UAT
Crédito Rural after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in Credito Rural
Manually create MD in Credito Rural
Run Smoke test
zTCD
(2)
BANKS
BANKS

## Slide 19: Easy IRPJ Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Easy IRPJ Support
Easy IRPJ after Go-live
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in Easy IRPJ
Manually create MD in Easy IRPJ
Run Smoke test
Easy IRPJ before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
zTCD
(2)
Easy IRPJ Support
zTCD

## Slide 20: VIM Satellite Landscape
TO-BE
AS-IS
FFU
EhP7 SP12
FEP
EhP7 SP12
POD
POI
POU
POP
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
Cutover Steps:
Business Cut Off
Move ECC TRs
Move GRCNFE TRs
Move PI/PO TRs
Run Smoke test
(2)
(4)
LND
POD
POI
POU
POP
(1)
LNI
LNU
LNP
GND
GNI
GNU
LNP
(5)
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
FFD
EhP7 SP12
FFT
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
RFC
RFC
RFC
RFC
ABAP Proxy
ABAP Proxy
ABAP Proxy
SEFAZ
WS
(3)
Review

## Slide 21: Biller Direct Solution Satellite Landscape
TO-BE
AS-IS
FFU
EhP7 SP12
FEP
EhP7 SP12
BDD Dev
BDx Prod
(1)
(3)
(5)
RFC
RFC
BDx IST
BDx UAT
RFC
RFC
(2)
FFD
EhP7 SP12
FFT
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
WAS JAVA 7.31
NDD NWDI
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
Extra pratica
SFDC
Components: FINBASIS 747 and FSCM_CCD 617
FSCM-BILLER DIRECT 6.35
SAP JAVA DATA DICTIONARY 7.30
Reverse Proxy Server
Cutover Steps:
Move ECC TRs
Assembly Developments and transport to other environments (dev, test, QA, prod)
Configure RFC connection between BDx Prod and Foundation
Install Security Certificate
Publish BD service over proxy on DMZ
Activate SSO
Run smoke test
CITIBANK
WS
BRADESCO
B.BRASIL
HTTP post
SSO Using
SAML 2.0
DMZ
https
(4)
(7)
(6)
BRADESCO
B.BRASIL
HTTP post
WAS JAVA

## Slide 22: TPS Pricing Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
TPS before Go-live
TPS
IST/UAT
TPS
after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in TPS Pricing
Manually create MD in TPS Pricing
Run Smoke test
zTCD
(2)
Review

## Slide 23: Commercial Satellite Systems Landscapes

## Slide 24: PecSYN Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
PecSYN
VPM PROD Before Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in PecSYN PROD
Manually create MD in PecSYN PROD
Run Smoke test
EBI
zTCD
Review
Pricing SPoT
PecSYN
CMT PROD Before Go-live
PecSYN
SIP PROD Before Go-live
Extrapratica
SPBF
EBI
Pricing SPoT
PecSYN
CMT PROD After Go-live
PecSYN
SIP PROD After Go-live
PecSYN
VPM PROD After Go-live
(3);
(4);
(5)
(3);
(4);
(5)
(2)
(2)
(2)

## Slide 25
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Plussoft
before Go-live
Plussoft Support
Plussoft
after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in Plussoft
Manually create MD in Plussoft
Run Smoke test
zTCD
(2)
Plussoft Support
zTCD
Plussoft Satellite Landscape
Review (in design)

## Slide 26
TO-BE
AS-IS
SPoT
before Go-live
SPoT
IST/UAT
SPoT
after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(2)
(3);
Cutover steps:
Business Cut Off
Implement Changes in SPoT
Run Smoke test
zTCD
(1)
SPoT
Support
zTCD
SPoT Satellite Landscape
Review
Vendavo
Vendavo
IST/UAT

## Slide 27
TO-BE
AS-IS
Teamspace
before Go-live
Teamspace
after Go-live
(2)
(3);
Cutover steps:
Business Cut Off
Implement Changes in Teamspace
Run Smoke test
Teamspace Satellite Landscape
Review (in design)
Teamspace
IST/UAT
(1)

## Slide 28: Disaggregation Satellite Landscape
TO-BE
AS-IS
BW
Disaggr. before Go-live
Disaggr.
after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(2);
(3)
Cutover steps:
Business Cut Off
Manually create MD in Disaggregation
Run Smoke test
zTCD
(1)
Review
SPBF
CMT
IBP

## Slide 29: Nutrade Satellite Systems Landscapes

## Slide 30: Gestão de Despesas Operacionais Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
GD Nutradebefore Go-live
GD Nutrade IST/UAT
GD Nutradeafter Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in GD Nutrade
Manually create MD in GD Nutrade
Run Smoke test
zTCD
(2)
Review

## Slide 31: Webmap & Feedsystem Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
Webmap before Go-live
Webmap IST/UAT
Webmap after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in WebMap
Manually create MD in WebMap
Run Smoke test
zTCD
(2)
Review

## Slide 32: Monitoramento Logístico Satellite Landscape
TO-BE
AS-IS
FFD
EhP7 SP12
FFT
EhP7 SP12
FFU
EhP7 SP12
FEP
EhP7 SP12
FBD
EhP7 SP12
FBI
EhP7 SP12
ML before Go-live
ML IST/UAT
ML after Go-live
LAD
EhP5
LAQ
EhP5
LAU
EhP5
BRP
EhP5
(1)
(3);
(4);
(5)
zTCD
zTCD
zTCD
zTCD
Cutover steps:
Move ECC TRs
Business Cut Off
Implement Changes in ML
Manually create MD in ML
Run Smoke test
RFC
(2)
Review
Armazéns