## Task_Table
ID | Name | Duration | Start | Finish | Predecessors
46 | Cut-Over Executions | 40 days | 28 February 2017 08:00 | 24 April 2017 17:00
47 | Technical cutover execution | 40 days | 28 February 2017 08:00 | 24 April 2017 17:00
48 | SAP Technical Activities | 36 days | 03 March 2017 08:00 | 23 April 2017 17:00
49 | Manual cutover setups Pre-Load before Transports | 1 day | 04 March 2017 08:00 | 04 March 2017 17:00
50 | Manual cutover setups Pre-Load after Transports | 1 day | 06 March 2017 08:00 | 06 March 2017 17:00
51 | Manual cutover setups after Master Data migration | 1 day | 25 March 2017 08:00 | 25 March 2017 17:00
52 | First Transport Window (MD and Org TR) | 1 day | 05 March 2017 08:00 | 05 March 2017 17:00
53 | Create printer queues in UNIX | 1 day | 20 March 2017 08:00 | 20 March 2017 17:00
54 | Create printer queues in UNIX | 1 day | 20 March 2017 08:00 | 20 March 2017 17:00
55 | Product Costing run | 1 day | 26 March 2017 08:00 | 26 March 2017 17:00
56 | Product Costing run | 1 day | 26 March 2017 08:00 | 26 March 2017 17:00
57 | Second Transport Window (Remaining TRs) | 1 day | 26 March 2017 08:00 | 26 March 2017 17:00
58 | CBP Activation | 1 day | 28 March 2017 08:00 | 28 March 2017 17:00
59 | Stop Hubbing Interface (Validate Date) | 1 day | 31 March 2017 08:00 | 31 March 2017 17:00
60 | BG Jobs Scheduling compl | 1 day | 02 April 2017 08:00 | 02 April 2017 17:00
61 | User Upload completion | 1 day | 03 March 2017 08:00 | 03 March 2017 17:00
62 | APO - DP Plan and Sales Data Final Update | 1 day | 04 April 2017 08:00 | 04 April 2017 17:00
63 | APO - Data Backup | 1 day | 04 April 2017 08:00 | 04 April 2017 17:00
64 | GPC Activation | 1 day | 06 April 2017 08:00 | 06 April 2017 17:00
65 | Synpro Activities | 1 day | 06 April 2017 08:00 | 06 April 2017 17:00
66 | EHS EBI Data Upload | 1 day | 09 April 2017 08:00 | 09 April 2017 17:00
67 | Manual cutover setups after complete Data migration | 2 days | 15 April 2017 08:00 | 16 April 2017 17:00
68 | Third Transport Window (Critical Objects) | 1 day | 16 April 2017 08:00 | 16 April 2017 17:00
69 | EHS Integration activation | 1 day | 16 April 2017 08:00 | 16 April 2017 17:00
70 | Printer Ready in FSAP (from LSAP) | 1 day | 16 April 2017 08:00 | 16 April 2017 17:00
71 | Hubbing Integration Activation | 1 day | 17 April 2017 08:00 | 17 April 2017 17:00
72 | APO (New CIF) Activation | 1 day | 17 April 2017 08:00 | 17 April 2017 17:00
73 | Mastersaf Connection to FEP (Short Downtime) | 1 day | 23 April 2017 08:00 | 23 April 2017 17:00
74 | SFDC Technical Activities | 31 days | 13 March 2017 08:00 | 24 April 2017 17:00
75 | Technical Cutover - SFDC BUILD | 1 day | 13 March 2017 08:00 | 13 March 2017 17:00
76 | Customer Update (Key fields) | 1 day | 20 March 2017 08:00 | 20 March 2017 17:00 | 157
77 | SFDC Realignment | 5 days | 21 March 2017 08:00 | 25 March 2017 17:00
78 | Product Update | 1 day | 26 March 2017 08:00 | 26 March 2017 17:00 | 160
79 | Interface Activation (non-Plene Prods) | 1 day | 26 March 2017 08:00 | 26 March 2017 17:00
80 | Customer Data Delta | 1 day | 27 March 2017 08:00 | 27 March 2017 17:00
81 | Delta Customer Realignement Check | 2 days | 29 March 2017 08:00 | 30 March 2017 17:00
82 | Interface Transport and setup | 4 days | 31 March 2017 08:00 | 05 April 2017 17:00
83 | Product Delta | 1 day | 06 April 2017 08:00 | 06 April 2017 17:00 | 161
84 | Delta + Plene Products realignement | 1 day | 06 April 2017 08:00 | 06 April 2017 17:00 | 161
85 | Territory Confirmation | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
86 | Exchange rate upload from FSAP | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
87 | User Release on SFDC | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
88 | Account Enrichment | 0,5 days | 08 April 2017 08:00 | 08 April 2017 12:00
89 | Account Validation | 0,5 days | 10 April 2017 08:00 | 10 April 2017 12:00 | 88
90 | Product Enrichment | 0,5 days | 09 April 2017 08:00 | 09 April 2017 12:00
91 | Product Validation | 0,5 days | 10 April 2017 08:00 | 10 April 2017 12:00 | 90
92 | Trading Price Load | 0,5 days | 10 April 2017 08:00 | 10 April 2017 12:00
93 | Price Book Load | 0,5 days | 10 April 2017 08:00 | 10 April 2017 12:00
94 | Historical Sales Order Load (LSAP, FSAP) | 1 day | 11 April 2017 08:00 | 11 April 2017 17:00
95 | Historical Shipment Load (LSAP, FSAP) | 1 day | 12 April 2017 08:00 | 12 April 2017 17:00
96 | Historical Commisions Load (LSAP) | 3 days | 12 April 2017 08:00 | 14 April 2017 17:00
97 | Historical Invoice Load (LSAP, FSAP) | 1 day | 13 April 2017 08:00 | 13 April 2017 17:00
98 | Final Validation | 1 day | 14 April 2017 08:00 | 14 April 2017 17:00
99 | Open Sales Order Load (EBI) | 1 day | 17 April 2017 08:00 | 17 April 2017 17:00
100 | Order interface activation | 1 day | 17 April 2017 08:00 | 17 April 2017 17:00
101 | Tier 1 Sales from IBP | 1 day | 20 April 2017 08:00 | 20 April 2017 17:00
102 | Open Shipping Load (EBI) | 1 day | 19 April 2017 08:00 | 19 April 2017 17:00
103 | Historical Commisions Load (EBI) | 1 day | 18 April 2017 08:00 | 18 April 2017 17:00
104 | Open Invoice Load (EBI) | 1 day | 18 April 2017 08:00 | 18 April 2017 17:00
105 | Final Validation | 3 days | 20 April 2017 08:00 | 24 April 2017 17:00
106 | Actuals from IBP | 1 day | 21 April 2017 08:00 | 21 April 2017 17:00
107 | Open Complaints Load (FSCM}) | 1 day | 22 April 2017 08:00 | 22 April 2017 17:00
108 | Go Live | 0 days | 24 April 2017 08:00 | 24 April 2017 08:00
109 | Vendavo Technical Cutover | 36 days | 05 March 2017 08:00 | 24 April 2017 17:00
110 | Constraints Sales Forecast | 1 day | 05 March 2017 08:00 | 05 March 2017 17:00
111 | Vendavo Technical Cutover | 1 day | 13 March 2017 08:00 | 13 March 2017 17:00
112 | Customer Data Available | 0 days | 20 March 2017 08:00 | 20 March 2017 08:00
113 | Foundation Z Tables Load (Vendavo) | 1 day | 26 March 2017 08:00 | 26 March 2017 17:00
114 | Product Interface Activation | 1 day | 26 March 2017 08:00 | 26 March 2017 17:00
115 | Product Upload (CP, Seeds, L&G Plene) | 1 day | 27 March 2017 08:00 | 27 March 2017 17:00
116 | Customer Master Upload (CBP) | 1 day | 28 March 2017 08:00 | 28 March 2017 17:00 | 58
117 | Vendavo System Lock | 0 days | 28 March 2017 08:00 | 28 March 2017 08:00
118 | Vendavo Data Validation | 1 day | 30 March 2017 08:00 | 30 March 2017 17:00
119 | Prices & CT loaded from LSAP > FSAP | 1 day | 05 April 2017 08:00 | 05 April 2017 17:00
120 | Customer aggregation template | 1 day | 05 April 2017 08:00 | 05 April 2017 17:00
121 | Vendavo System Lock | 4 days | 05 April 2017 08:00 | 10 April 2017 17:00
122 | Upload Contracts (Template) | 1 day | 05 April 2017 08:00 | 05 April 2017 17:00
123 | Upload Rebate Contracts (Template) | 1 day | 05 April 2017 08:00 | 05 April 2017 17:00
124 | Product Data (EBI) | 1 day | 06 April 2017 08:00 | 06 April 2017 17:00
125 | Product Data Validation | 1 day | 06 April 2017 08:00 | 06 April 2017 17:00
126 | Exchange Rate Upload (Quantum) | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
127 | Commercial Exchange Rate Upload | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
128 | Rebates template Prices & CT to Glovia | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
129 | Delta Account Plans Load | 1 day | 08 April 2017 08:00 | 08 April 2017 17:00
130 | Delta Campaigns Plans Load | 1 day | 08 April 2017 08:00 | 08 April 2017 17:00
131 | Trading price load into staging table to use interface to send SFDC | 1 day | 09 April 2017 08:00 | 09 April 2017 17:00
132 | Territory information Business > Vendavo | 1 day | 10 April 2017 08:00 | 10 April 2017 17:00
133 | User Load into Vendavo | 1 day | 10 April 2017 08:00 | 10 April 2017 17:00
134 | User Sync with SFDC and Vendavo (and Glovia?) | 1 day | 10 April 2017 08:00 | 10 April 2017 17:00
135 | New Campaigns Loaded from SFCD | 1 day | 24 April 2017 08:00 | 24 April 2017 17:00
136 | New Account Plans Loaded from SFDC. | 1 day | 24 April 2017 08:00 | 24 April 2017 17:00
137 | Loads from SFDC - Commitments, Consumptions, Stock | 1 day | 24 April 2017 08:00 | 24 April 2017 17:00
138 | EBI Technical Cutover | 7 days | 06 April 2017 08:00 | 14 April 2017 17:00
139 | Load all MD from FOU and MDM | 1 day | 06 April 2017 08:00 | 06 April 2017 17:00
140 | GPC/Synpro loads after budgeting and forecast runs | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
141 | Historical and Actuals Migration | 2 days | 07 April 2017 08:00 | 08 April 2017 17:00 | 179
142 | Forecasting Customer Load | 1 day | 14 April 2017 08:00 | 14 April 2017 17:00 | 158
143 | Planning combinations | 1 day | 14 April 2017 08:00 | 14 April 2017 17:00
144 | Glovia | 7 days | 07 April 2017 08:00 | 15 April 2017 17:00
145 | Prices & CT to Glovia | 1 day | 07 April 2017 08:00 | 07 April 2017 17:00
146 | Customer Upload (SFDC) | 1 day | 09 April 2017 08:00 | 09 April 2017 17:00 | 89
147 | Material Upload (SFDC) | 1 day | 09 April 2017 08:00 | 09 April 2017 17:00 | 91
148 | Contract Upload (FSAP) | 1 day | 15 April 2017 08:00 | 15 April 2017 17:00
149 | Sales Orders (FSAP) | 1 day | 15 April 2017 08:00 | 15 April 2017 17:00 | 186
150 | VIM
151 | CARD | 5 days | 10 April 2017 08:00 | 15 April 2017 17:00
152 | Credit Management Limit Validation | 3 days | 10 April 2017 08:00 | 12 April 2017 17:00
153 | Manual Cutover Activities | 1 day | 15 April 2017 08:00 | 15 April 2017 17:00
154 | Data Migration | 34 days | 28 February 2017 08:00 | 17 April 2017 08:00
155 | Master Data Uploads to Target System | 26 days | 28 February 2017 08:00 | 05 April 2017 08:00
156 | Customer Master Data extraction | 1 day | 18 March 2017 08:00 | 18 March 2017 17:00
157 | Customer Master Data Loaded | 2 days | 18 March 2017 08:00 | 20 March 2017 17:00
158 | Customer master Data Validated | 0 days | 29 March 2017 08:00 | 29 March 2017 08:00 | 177
159 | Product Data Extraction | 1 day | 28 February 2017 08:00 | 28 February 2017 17:00
160 | Product Data Loaded | 0 days | 25 March 2017 08:00 | 25 March 2017 08:00
161 | Product data Validated | 0 days | 05 April 2017 08:00 | 05 April 2017 08:00
162 | Master Data Migration conclusion | 0 days | 05 April 2017 08:00 | 05 April 2017 08:00 | 161;158
163 | Transactional Data Mi | 15 days | 27 March 2017 08:00 | 14 April 2017 17:00
164 | Transactional Data Extraction | 6 days | 27 March 2017 08:00 | 03 April 2017 17:00
165 | AP Data Upload - Open Items | 1 day | 11 April 2017 08:00 | 11 April 2017 17:00
166 | AR Data Upload - Open Items | 1 day | 11 April 2017 08:00 | 11 April 2017 17:00
167 | GL Data Uploaad | 1 day | 11 April 2017 08:00 | 11 April 2017 17:00
168 | P&S Inventory Load | 1 day | 12 April 2017 08:00 | 12 April 2017 17:00
169 | Sales Order Load | 1 day | 14 April 2017 08:00 | 14 April 2017 17:00
170 | Data Migration complete | 0 days | 17 April 2017 08:00 | 17 April 2017 08:00 | 155;163