## Slide 1
Infosys proposal for
Change Request : Monitoramento Logístico
Version 1.0
24 November 2016
Internal

## Slide 2
TABLE OF CONTENTS
Executive Summary
Scope
Out of Scope
Assumptions
Project Plan & Investment
Indicative Stream wise Effort Split
Commercials Conditions

## Slide 3
Platform 17 (PF17) will be platform to transform LSAP crop protection system in Foundation system, and following change requests has to be complete before project go live:
Monitoramento Logístico:
Executive Summary
Scope
  Split Monitoramento Logistico App of Extrapratica.
  Remove All SAP interactions.
  Remove all dependencies with ClickCommerce Authentication.
  Create Simple Authentication Login Screen.
  Create Load Interface for master data and workflow data via flat file.
  All functionalities related Cotton Commodity will be removed.
  Keep remaining functionalities in the application.

## Slide 4
Implementation Activities
  Design and Requirements Gathering
  Server/Enviorment Setup
  Build / LSAP & FOU and Unit Test
  IST Test Preparation/Execution
  UAT Execution & Issue resolution
  Cutover Preparation / Go live
  Go-Live and Hyper care
Scope

## Slide 5
Business sign off of any deliverable (Documentation , UAT results, etc.)
Training Content preparation & User Training
Planning and Organizing Fit Gap workshops
BPA activities
UAT execution
Out of Scope

## Slide 6
Assumptions
Syngenta will ensure provide infrastructure and systems accesses to Infosys resources assigned to this project.
Designated Syngenta´s business/key users should be available during UAT.
Any change on the requirements will generate effort new estimation in times and efforts.
Any required Master Data update/upload should be performed by Syngenta.
Data generation for UAT will be responsability of Syngenta
Training to End users will be performed by Syngenta
Methodolygy / IT Processes & Approvals / Documentation Templates to use in the project follows Syngenta´s once.
All project related communication will be done using English language
São Paulo (Infosys Office or Syngenta / CENESP office) is assumed as project location, any travel to other local can be charge extra values.
  This Application will be available for short period (9 months).
  There will not be enhancements involved in a current process.
  There will not be changes in the current business logic.
  This application will be available (accessible) only in Syngenta Intranet.
  The flat files of master data and workflow will be provided by Syngenta business area.

## Slide 7
Monitoramento Logístico:
Timelines Estimate: 8 Weeks (40 Workdays)
Project plan & Investment
Description | BRL (*)
Change Request: Monitoramento Logístico | 115.095
* Values without tax | 

## Slide 8
Chart: 
| Sr. Non SAP Resource | Project Manager
Column1 | 40 | 20
Indicative Stream wise Effort Split

## Slide 9
Detailed conditions will be established in the SOW, which will follow MSA guidelines.
Workflow approval to SOW has to be completed to start project on expected date.
This commercial proposal has valid for 5 days from this current date.
Any change in the scope presented, it will be void and a new proposal will be submitted for customer analysis.
The adoption of this proposal should be directed by Estimation Tool, considering information of “Global Business Owner" and "Basel Cost Center" to this enclosure.
Infosys garantees correct Bill To and Bill From Entities in the SoWs and Invoicing documents and Syngenta garantees that budget is allocated accordingly. Ex: Bill to/Bill from – Syngenta Basel/Infosys IN, Syngenta Brazil/Infosys Brazil, Syngenta Argentina/Lodestone Argentina, etc. At the time Infosys requests an approvers list for any SoW, the funding source (ex.: SBS vs non-SBS) should also be considered in the response.
Commercials Conditions